## Grouped Tasks
GenView TASKS regarding pathway part

TASK	PRIORITY
ViewRep
Extend Date Explorer (pathway list, view list)	1
MIDI interface + Mixer ViewRep	?
ViewRep for creating new Sets/Storages/Selections	3
Drag & drop of data on view	3
Command implementation for each important ViewRep with key value pair	1
New ViewRep for Patient information	2
Table for viewing all patient data	2

2D PathwayViewer
Connection of pathway nodes to foreign nodes (concept!)	2
Mouse-over item highlighting (+ identical visible items)	1
Correct pathway neighborhood visualization (i.e. indirect connections)	2
New JGraph pathway layer view	3
Semantic-zoom, collapsing (concept!) - also in OpenGL	4

Data structure
Implementing selections data structure (for pathways, heatmaps, etc.)	1
Enyzme -> Gene mapping (request a special mapping from Mr. Asslaber)	1
New edge implementation to consider multiple connections	3
Search for Enzyme/Compound/Gene + highlighting	3
Import SBML data	4
Hierarchical graph data structure (for dendrograms and pathway levels)	2
Consistent ID management	2

OpenGL pathways
Multiple pathway layer view - including cross-references	1
Evaluation and integration of advanced OpenGL visualization techniques	1
(Radial Layout, TILT plane, Bifocal lense, Interring, Treemap, ThemeRiver, etc.)
OpenGL highlight of selections	2
Improve OpenGL pathway view (styles, alignment, etc.)	3
Pathway image loading in OpenGL pathway view (TGA - with transparency)	4
Cone Tree concept (some kind of)	5

WEKA
Integration of pathway data	1

Research
Further research to keep global view on topic	1
Papers planning	1
Meeting with LKH partners - find out useful pathway/heatmap scenario	1

Others
Progress bar on application bootstrapping (sticky)	4
Command Serialization (for exporting/saving and network app.)	4
Extending CommandManager with seperate UNDO stacks for data and view	3
Multiple work station setup	4
Multi-monitor setup - including new input devices	2
Evaluation GO (GeneOntoloy)	3

## Ranking
	GenView TASKS regarding pathway part

	TASK	PRIORITY
1	Further research to keep global view on topic	1
2	Implementing selections data structure (for pathways, heatmaps, etc.)	1
3	Enyzme -> Gene mapping (request a special mapping from Mr. Asslaber)	1
4	Paper planning	1
5	Mouse-over item highlighting (+ identical visible items)	1
6	Command implementation for each important ViewRep with key value pair	1
7	Multiple pathway layer view - including cross-references	1
8	Extend Date Explorer (pathway list, view list)	1
9	Integration of pathway data in WEKA	1
10	Evaluation and integration of advanced OpenGL visualization techniques	1
	(Radial Layout, TILT plane, Bifocal lense, Interring, Treemap, ThemeRiver, etc.)
11	Meeting with LKH partners - find out useful pathway/heatmap scenario	1
12	OpenGL highlight of selections	2
13	Hierarchical graph data structure (for dendrograms and pathway levels)	2
14	Connection of pathway nodes to foreign nodes (concept!)	2
15	Correct pathway neighborhood visualization (i.e. indirect connections)	2
16	New ViewRep for Patient information	2
17	Table for viewing all patient data	2
18	Multi-monitor setup - including new input devices	2
19	Consistent ID management	2
20	ViewRep for creating new Sets/Storages/Selections	3
21	Drag & drop of data on view	3
22	New edge implementation to consider multiple connections	3
23	Search for Enzyme/Compound/Gene + highlighting	3
24	Improve OpenGL pathway view (styles, alignment, etc.)	3
25	New JGraph pathway layer view	3
26	Extending CommandManager with seperate UNDO stacks for data and view	3
27	Evaluation GO (GeneOntoloy)	3
28	Progress bar on application bootstrapping (sticky)	4
29	Pathway image loading in OpenGL pathway view (TGA - with transparency)	4
30	Command Serialization (for exporting/saving and network app.)	4
31	Multiple work station setup	4
32	Semantic-zoom, collapsing (concept!) - also in OpenGL	4
33	Import SBML data	4
34	Cone Tree concept (some kind of)	5
35	MIDI interface + Mixer ViewRep	?

## Sheet3
Tentative Feature List

FEATURE	STATUS	PRIORITY
2D Pathway Editor
Visualization of single pathway as Graph	Completed	1
Zoom in / zoom out	Completed	3
Filtering of edge connections (reactions & relations)	Completed	3
Interactive pathway overview map	Completed	2
Showing neighborhood using different distance (1, 2, 3)	Completed	2
Switching between pathways	Completed	1
Clickable reference pathway map image	Completed	2
Add/edit nodes of different type	Pending	4
Add/edit node connection	Pending	4
Remove nodes and eges	Pending	4
Rearrange pathway nodes	Pending	4
Apply and visualize additional pathway information	Pending	2
(e.g. co-factors, regulation/activation, energy level, energy consumption)

3D OpenGL pathway view
Visualization of single pathway as graph in OpenGL	Completed	1
Multiple pathway layer view	Completed	1
Pathway texture loading in OpenGL pathway	Pending	2
Mouse-over item highlighting	Pending	1
Picking of Enzymes/Compounds	Pending	1
Visualizing cross references between pathway layer (using a simple line connection)	Completed	1
Visualization of neighborhood using different distance	In progress	2
Radial Layout Visualization	Pending	1
Improved element highlighting (e.g. glowing nodes, pulsing connections)	Pending	2

Data structure
Importing pathway data from XML file	Completed	1
Enzyme -> Gene mapping	In progress	1
Pathway data integrated in WEKA	Pending	1
Selection of enzymes and compounds (synchronized with other views)	In progress	1

Application framework
Data explorer view	Completed	1
Integrated Set/VirtualArray/Storage data in date explorer	Completed	2
Integrated patient data in data explorer	Pending	3
Integrated pathway list in data explorer	Pending	2
Integrated list of views and current selections (important for update behaviour)	Pending	1
Full customizeable GUI layout and views via XML file	Completed	1
Drag & drop of data on view	Pending	2
Search for Enzyme/Compound/Gene + Highlighting	Pending	3
Loading of additional pathway information in integrated browser view	Completed	2

Others
Determine use case	Pending	1

	Completed
	Pending
	In progress

Evaluation and integration of advanced OpenGL visualization techniques
(Radial Layout, TILT plane, Bifocal lense, Interring, Treemap, ThemeRiver, etc.)

OpenGL highlight of selections
Hierarchical graph data structure (for dendrograms and pathway levels)
Connection of pathway nodes to foreign nodes (concept!)
Correct pathway neighborhood visualization (i.e. indirect connections)
New ViewRep for Patient information

Multi-monitor setup - including new input devices
Consistent ID management
ViewRep for creating new Sets/Storages/Selections

New edge implementation to consider multiple connections

Improve OpenGL pathway view (styles, alignment, etc.)
New JGraph pathway layer view
Extending CommandManager with seperate UNDO stacks for data and view
Evaluation GO (GeneOntoloy)
Progress bar on application bootstrapping (sticky)

Command Serialization (for exporting/saving and network app.)
Multiple work station setup
Semantic-zoom, collapsing (concept!) - also in OpenGL
Import SBML data
Cone Tree concept (some kind of)
MIDI interface + Mixer ViewRep