## Sheet1
TASK LIST	Status	Duration	Percent
		weeks	% finished
Cerberus Application
Basic class design	DONE	2	100%
Design document	DONE	0,5	100%
Integration of components into system backbone	DONE	0,5	100%
Interaction between views (Updates, synchronization, etc.)	ONGOING	1	30%
Hierarchical Data Explorer (Set/Selection/Storage)	DONE	0,5	100%
Graph Visualization of Data Structure (Set/Selection/Storage)	PLOT	1	0%
Prepare demo for collaboration partners	ONGOING	2	70%
Automatic layouting of views	ONGOING	1	70%
Extending:
Adding SWT as GUI library to existing Swing GUI	DONE	2	100%
XML Bootstrapping	DONE	2	100%
Export / Import of full application status at any time (XML read, write, bootstraping )	ONGOING	2	30%
Distributed application	ONGOING	1	20%

Pathway
Market-analysis of existing gene databases / pathway tools	DONE	0,2	100%
Import Pathway from KEGG XML file (existing package)	DONE	0,5	100%
User editable pathways	ONGOING	0,5	100%
Pathway drawing tool (maybe usage of external open source tool)	SCHEDULED	1	0%
Integrating pathway data into WEKA	SCHEDULED	2	0%
Multidimensional/hierarchical Pathways	SCHEDULED	3	0%

Research
Evaluation of user interface design (Top projection, etc.)	SCHEDULED	2	0%
Evaluation of new/alternative visualization techniques (2.5D Heatmap, etc.)	SCHEDULED	3	20%
Evaluation of pathway relevance for clustering	SCHEDULED	2	10%